## Software Defect Report Template
SOFTWARE DEFECT REPORT TEMPLATE |  |  |  | http://bit.ly/2UqesFD
DEFECT ID | TITLE | DESCRIPTION / SUMMARY | ENVIRONMENT | STEPS TO REPRODUCE | SCREENSHOT | DEFECT SEVERITY | DEFECT PRIORITY | REPORTED BY | ASSIGNED TO | STATUS | RESOLUTION | DATE REPORTED | DATE OF FIX | SEVERITY | DEFECT PRIORITY | STATUS
1 | Wrong README.txt file encoding | When opened, the file is saved as in UTF-8 encoding, even though it's encoded in Cyrillic (cp1251) | README | Open README.txt in a text-editor or text-reader | https://i.imgur.com/pqhuIfo.png | Low | Low | O. T. |  | Open | Rewrite file in UTF-8 | 2021-09-04 |  | Showstopper | Critical | Open
2 | Help > Contents… menu item doesn't work | Instead of oppening "operational information on working with the controls on the form", it redirects to https://support.microsoft.com/en-us/topic/error-opening-help-in-windows-based-programs-feature-not-included-or-help-not-supported-3c841463-d67c-6062-0ee7-1a149da3973b | App | Choose Help > Contents… menu item | https://i.imgur.com/UOZxqBO.jpeg | Low | Low | O. T. |  | Open | Make that help window open |  |  | Major | High | Resolved
3 | Save/Open behaviour isn't specified |  | Specification |  |  |  |  | O. T. |  | Open |  |  |  | Minor | Medium | Closed
4 | No "<none>" filter in mixed mode |  | App | Choose both "Alphabetic" and "Numeric" modes, open "Range" dropdown, find no "<none>" filter | https://i.imgur.com/QUR7Nk4.png | Minor | Medium | O. T. |  | Open |  |  |  | Low | Low
5 | Filter with no label that does nothing | Probably connected with the ISSUE 4 | App | Choose any "Alphabetic" or "Numeric" mode, open "Range" dropdown, find no "" filter that doesn't change the last choosen filter | https://i.imgur.com/MF1merw.png | Minor | Medium | O. T. |  | Open
6 | It's possible to add empty lines to the list | Minimal length of a line is 1, so it mustn't be possible to add empty lines to the list | App | Choose any mode, do not enter anything in the textbox, click "Add to List" button | https://i.imgur.com/hlFYAXY.jpeg | Minor | Medium | O. T. |  | Open
7 | It's possible to add 10000 to the list in the numeric mode | Number must be in the range 0-9999, but it's possible to enter 10 000 | App | Enter 10000 in "Numeric" or "Alpabetic" mode, click "Add to List" button | https://i.imgur.com/YvJavMu.jpeg | Minor | Medium | O. T. |  | Open
8 | Mixed mode numeric filters behaviour isn't specified | For example, how filter "0-100" must behave in a situation of a mixed mode | Specification |  |  | Minor | High | O. T. |  | Open
9 | Program version hasn't been updated | Should be equal to "1.98" | App | Open Help > About ListBoxer… | https://i.imgur.com/Wc006aQ.jpeg | Low | Low | O. T. |  | Open
10 | Clicking list box item behaviour isn't specified | Currently it pastes a clicked list item content into text box | Specification | Double click on list box item | https://i.imgur.com/5oxplHY.jpeg | Low | Low | O. T. |  | Open
11 | List box scroll behaviour is laggy | List box frizzes a bit when scrolled | App | Add enough items to the list to make scrollbar appear and try to scroll it |  | Low | Low | O. T. |  | Open
12 | List item is deleted when file is saved | After saving and opening a file, an item from the list box disappears | App | Save, open file |  | Major | Critical | O. T. |  | Open
13 | Copy/Cut are anactive | Edit > Copy/Cut options aren't active when either textbox text or list box item is selected. | App | Select text in textbox/item in the list box, try to use Edit > Copy/Cut options | https://i.imgur.com/trMlzmo.png | Minor | Low | O. T. |  | Open
14 | Paste option is inactive | Edit > Paste option isn't active when there's text in the clipboard | App | Copy any text, focus textbox, try to paste text using Edit > Paste |  | Minor | Low | O. T. |  | Open
15 | Spelling mistake | Edjt instead of Edit | App |  | https://i.imgur.com/Ro9Duc5.jpeg | Low | Low | O. T. |  | Open
16 | Items starting with a number aren't displayed in "Alphabetic" mode | While items that contain numbers are displayed, items that start with a number and contain characters don't appear in the list. Connected with the ISSUE 8 | App | Enter items - "1a", "a1". Choose "Alphabetic" mode and filter "All". "a1" - visible, "1a" isn't |  | Minor | Medium | O. T. |  | Open
17 | Text box in numeric mode accepts more than 4 digits | It's possible to type 8 digits in text box while numbers 0 to 9999 are accepted. | App | In "Numeric" mode type 8 digits | https://i.imgur.com/GQK4CaN.jpeg | Low | Low | O. T. |  | Open | Limit number of possible digits in "Numeric" mode to 4
18 | Typo in filter dropdown | Last filter item must start from 301, not 300 | App |  | https://i.imgur.com/GQK4CaN.jpeg | Low | Medium | O. T. |  | Open
19 | Incorrect order in "descending" sort mode |  | App | Type in numbers, choose "descending" sort mode | https://i.imgur.com/VLHZCkQ.jpeg | Minor | Critical | O. T. |  | Open
20 | When file opened mode isn't restored | When file is opened, it's expected that the same mode that was chosen before saving the file is selected, instead both modes are active | App | Choose a mode, save file, open file |  | Minor | High | O. T. |  | Open | Remember an active mode when saving a file
21 | It's impossible to restore insertion order after choosing any sorting mode | When application is opened, no soring mode is chosen, so order of insertion is preserved. When any of the modes is selected it's impossible to unselect to restore original order | App | Open app, enter list items, choose sorting mode, try to restore order of insertion | https://i.imgur.com/opizZzS.jpeg | Minor | Medium | O. T. |  | Open
22 | When file opened sorting mode isn't restored | When file is opened, it's expected that the same sorting mode that was chosen before saving the file is selected, instead no or chosen before file opening mode is selected | App | Choose a mode, save a file, choose another sorting mode, open the file |  | Minor | High | O. T. |  | Open | Remember an active sorting mode when saving a file
23 | Undo option in the menu isn't deactivated after the first undo | After a user undo an action, he can't undo any more, so the item is expected to be grayed out and disabled | App | Undo an action, open "Edit" menu item, "Undo" option isn't grayed out | https://i.imgur.com/bdN7HLr.jpeg | Low | Low | O. T. |  | Open
24 | Error pop ups after installation cancellation | When installer is launched, it shows a windows with two buttons and a warning message, if user chooses "Exit setup" and then clicks "Yes" error pops up | Setup |  |  | Minor | Medium | O. T. |  | Open
25 | Application removal not responding | After user cliks "Exit setup" and "Yes", Application Removal window pops up and shows not responding | Setup |  | https://i.imgur.com/eduWvsU.jpeg | Showstopper | Medium | O. T. |  | Open
26 | ListBoxerSpecification.docx doesn't open |  | Specification |  | https://i.imgur.com/gkSVaK5.jpeg | Low | High | O. T. |  | Open
27 | Change directory window scroll animation is reversed | When user clicks "Change directory" during application setup and tries to scroll the view with directories, animation appers to be reversed | Setup | Click setup, click "Yes" on warning notice, click "Change directory", scroll "Directories" view |  | Low | Medium | O. T. |  | Open
28 | Uninstaller doesn't delete ListBoxer.exe file | When user is prompted to choose whether to delete "ListBoxer.exe", even if user clicks remove, the files stays in its place | Remove | Run uninstaller, proceed with uninstallation, when promted whether to remove files say "Remove" to all, check folder |  | Low | Low | O. T. |  | Open
29 | "Choose Program Group" window appears in the left top part of the screen | When user clicks setup after choosing installation directory, "Choose Program Group" appears and is located in the top left part of the screen | Setup |  | https://i.imgur.com/HKKi9x5.jpeg | Low | Low | O. T. |  | Open
30 | "About LisBoxer" window appears in the left top part of the screen | When opened, Help > About ListBoxer… appears in the left top cornet. CONNECTED TO 29 | App |  |  | Low | Low | O. T. |  | Open